## Slide 1: Review: The 2021 HIV Planning Group
~Goals and Workplan~
HPG
2021
UPDATE?

## Slide 2: HPG Goals
2021 HPG Goals
Continue to evaluate progress on the Current (2017) IHPCP
Support and inform 2021 IHPCP development
  Intersectional issues (new issues that need to be addressed)
  Priority Setting
  Assessing, reviewing, improving Plan drafts/sections
Facilitate Stakeholder Engagement
  About the mission/work/goals/ of the HPG
  About the IHPCP
  About people’s needs and experiences
Advise the Division of HIV Disease in all applicable matters
  IHPCP (see above)
  CQM
  HIV and PLWH-related issues in the state
Discussed, edited and approved during the November 2020 HPG Meeting
Updates can be suggested by the HPG (to the Steering Committee) or presented by the Division
Notes: As you may remember from the February meeting, aspects of the HPG’s workplan have been delayed by changes in Federal (CDC etc.) planning updates. The DOH and HPG are still waiting for this guidance to be released. Because this plan (again, from the January HPG meeting) was discussed, revised and approved in November of 2020 by the HPG, the Steering Committee felt it was important for the whole group to revisit and potentially revise this workplan since the changing federal guidance is delaying the timeline for the new Integrated Plan.

## Slide 3: 2022 IHPCP Development
  Finish Priority Setting (PS) process
    View remaining presentations
    Support additional consumer feedback opportunities
    Review previous data/presentations
    Vote on Priorities
  Advise: Monitor/support/revise 2022 IHPCP Drafting
    Receive regular updates on draft process
    Review and edit portions (via Assessment Subcommittee and full group)
    Participate and promote stakeholder engagement feedback
    Vote on concurrence
Goal 2: Inform 2022 IHPCP
Notes: Waiting for new guidance around the IHPCP primarily impacts two areas: the Priority Setting work (for which the HPG is responsible), and the development and review of the IHPCP (which the Division, HPCP, and HPG all work on together in different ways).

## Slide 4: HPG 2021 Timeline
Approved Timeline
Date/Event: | Location: | Business to be accomplished:
February HPG Meeting | Virtual | Orientation 2021 plan review Final PS data presentations Subcommittee time IHPCP progress report
May HPG Meeting | Virtual | Review all PS data Vote on priorities Subcommittee time IHPCP updates and section review IHPCP Stakeholder engagement
Summer Townhall | Erie? | Community engagement: update on HPG work/feedback Day 2: HPG business
August HPG Meeting | TBD | Subcommittee work IHPCP Stakeholder review process
September Townhall | Delaware County? | Community engagement: update on HPG work/feedback Day 2: HPG business
November | TBD | Subcommittee time IHPCP Stakeholder review process Review final draft of IHPCP!
Revised Timeline
Date/Event: | Location: | Business to be accomplished:
February HPG Meeting | Virtual | Orientation 2021 plan review Final PS data presentations Subcommittee time IHPCP progress report
May HPG Meeting | Virtual | Subcommittee time IHPCP updates and section review IHPCP Stakeholder engagement Final PS data presentations Department updates/Orientation
Summer Townhall | No? | Community engagement: update on HPG work/feedback Day 2: HPG business
August HPG Meeting | TBD | Subcommittee work IHPCP guidance update and planning Stakeholder and PS engagement review/planning
September Townhall | Delaware County? | Community engagement update Day 2: HPG business HPG: Review all PS materials
November | TBD | Subcommittee time IHPCP Stakeholder review process Review draft of IHPCP Vote on final Priorities
Notes: Here you can see the current, approved timeline last year’s HPG developed and approved. On the right is one example/starting point of how the plan could be updated to reflect our waiting for the new IHPCP Guidance. No deadline is yet known for the new IHPCP, but it will undoubtedly not be any earlier than mid-2022. Hopefully this slide can serve as a foundation for discussion around what the members would like to see and do in the coming year. (Remember that this does not include, but leaves room for, new items/issues that the members or Division may raise as the year goes on as well as the work of workgroups since that’s primarily outside of regular meetings.)

## Slide 5: Discussion and Questions